## August 2018
Work Record Sheet ¦ NSKFDC App ¦ August, 2018
S.No | JIRA ID | Activity/Story Description | Owner (S&B) | Hours Spent | SCGJ POC
1 | NA-2 | As a product owner, I want to upload various documents against the specific batch ID so that the scgj admin can view the uploaded documents | Prateek | 9 | Prashant
2 | NA-28 | As a Product Owner, I want to import .xlsx file and few columns of information into the system so that I can store data into the system | Prateek | 19 | Prashant
3 | NA-31 | As a product owner, I want NSDC registration number field in Generate credentials to be unique, so that credentials with same NSDC number can not be generated again. | Priyanka | 3 | Prashant
4 | NA-38 | As a product owner, I want a final batch Report pdf to be generated, so that TP can generate a defined format report only by entering required data | Priyanka | 7 | Prashant
5 | NA-41 | As a product owner, I want a submit batch functionality, so that TP can store the data into system | Priyanka | 4.5 | Prashant
6 | NA-72 | As a product owner, I want to update the targets to be achieved by TPs, so that TP can get updated targets detail from system & train according to it | Prateek | 3.5 | Prashant
7 | NA-204 | As a product owner, I want to get the current background image of Home page to be replaced with the suggested image after the first demo to SCGJ. | Priyanka | 3 | Prashant
8 | NA-206 | As a product owner, I want a user to create a batch on clicking generate batch id, only after confirming it using the pop up, so that user does not generate batch without awareness. | Priyanka | 4 | Prashant
9 | NA-207 | A a product owner, I want a Unique batch Id for each training partner to be generated, which should have Training partner name & the batch number | Prateek & Priyanka | 16 | Prashant
10 | NA-209 | A a product owner, I want a button to generate candidate excel sheet having candidate details of a batch id, so that TP can get the already entered candidate details & continue updating the candidate details. | Priyanka | 8 | Prashant
11 | NA-210 | As a product owner, I want error messages to be shown while importing excel sheet stating the row and column number of excel sheet, so that TP get to know the specific error & can correct it | Prateek | 2 | Prashant
12 | NA-211 | As a product owner, I want the format of minutes of selection committee meeting report to be changed, so that the format we can only be generated for the report. | Priyanka | 4 | Prashant
13 | NA-212 | As a product owner, I want the name of file getting downloaded in generate documents and View documents should have batchId, so that it is easier to identify the file belongs to which batch | Prateek | 3 | Prashant
14 | NA-213 | As a business analyst, I want to prepare for training of the application so that, I can train SCGJ's representatives on the application | Prateek | 3 | Prashant
15 | NA-216 | As a Training Partner, I want to update/insert the SCGJ Batch number against the batch Id so that I can use the batch number to generate the Final Batch Report | Prateek & Priyanka | 12 | Prashant
16 | NA-217 | TP should see SCGJ batch number assigned to them while genrating final batch report | Prateek | 5 | Prashant
17 | NA-223 | As a developer, I want to Build understanding of change requests from the client, so that development approach can be identified | Prateek & Priyanka | 10 | Prashant
18 | NA-227 | As a business analyst, I want to do Requirement Capturing ¦ Confluence Update ¦ Design Development ¦ Development Approach, so that developer can get ready to work on new change request | Prateek | 5 | Prashant
19 | NA-228 | As a business analyst, I want to prepare for the demonstration of SCGJ/Safai Karamchari - app, So that the demo can be executed smoothly | Prateek | 4 | Prashant
20 | NA-229 | Training of SCGJ's Representative and Demo of application to NSKFDC | Prateek | 6 | Prashant
21 |  | Testing | Prateek & Priyanka | 26 | Prashant
|  |  | Total Time Spent | 157