## Sheet1
Change Requests for SCGJ - App (21-08-2018)
Screen | Module | Change Request | Status | Estimation | Priority
SCGJ | Generate Credentials | Generated Credentials table to be populated as soon as the credential is generated | CR
|  | Add column for target allocated before generated on column in generated credentials table | CR
|  | Search the generated credentials using only the digits of NSDC Reg. Number | CR
|  | Change password functionality for training partner | CR
| FAQs | dynamic FAQs for SCGJ | CR
| Mail to SCGJ | Mail should be sent to SCGJ as soon as a training partner uploads any document | CR
| Upcoming assessments | Details of the upcoming assessments to be shown to SCGJ for each training partner | CR
Training Partner | Master Sheet Import | Format of Batch-Id : Initals of Tp/Municipality/id(number) |  | 8
|  | A pop-up should appear which asks for the name of municipality while creating a batch |  | 6
Age should be automatically calculated from date of birth in the master sheet
|  | Master Sheet Import history | CR
|  | Any candidate having age less than 18 should not be allowed to enter the system |  | 2
|  | Show a progress bar/gif while the file is being uploaded |  | 1
|  | Rename employer name to Spoc Name & Employer Number to Spoc Number in batch details |  | 0.5
| Generate Reports | Implement new template for minutes of selection committee (landscape format) |  | 8
|  | Implement new template for occupation certificate (landscape format) |  | 8
|  | Add column for view/download reports from audit table | CR
|  | Signature box for the gazetted officer should be present at bottom left corner of each page in Occupation Certificate |  | 4
|  | Sign and Stamp section should be present on the bottom right of each page in occupation certificate |  | 4
|  | Increase the height of rows in occupation certificate so that the thumb impressions do not over lap |  | 2
| Generate Batch Report | Enter the information of pay out to candidates that will be used in final batch report (Discuss with Kamal) | CR
Meeting with TP & NSKFDC (06-09-2018)
Additional functionalities | Requests by NSKFDC & SCGJ & TP | Functionality to generate reports on how many trainings have been completed till now (After every 15 days) - Discuss Req
Make the system flexible to handle the data for waste pickers (Reports,excels to be uploaded) - Depends on the req.
Upload Aadhar card and bank details of candidates in the system (Details are already being added in the master sheet)
|  | dynamic FAQs for SCGJ & NSKFDC (Discussion with SCGJ & NSKFDC) |  | 20
|  | Upload the details of Manual Scavengers and their dependents on our portal ( Requested by Mr. Narayan) |  | 6
|  | Hyperlink to SCGJ website | Done | 0.5
|  | Total work excluding the functionalities to be discussed |  | 120 hrs
Business Opportunities from the meeting (06-09-2018)
Presentation on financial schemes of NSKFDC to be prepared by SCGJ - Opportunity for BSC Wing
NSKFDC wants Safai Karamcharis to share the experience of training so that NSKFDC can project the parameters to Ministry on what made the training better - Opportunity for Data Analytics wing
SCGJ will be training the supervisors of the municipality on the basis of QP - Opportunity for BSC
Workshop on Life Skills to be carried out by SCGJ for the Safai Karamcharis - Opportunity for MD Wing
Management of Dependents of the Manual Scavengers on what kind of trainings, Skilling they want & share it with the other sector skill councils - Emphasised by Mr. Narayan
Action Items for the meeting (06-09-2018)
Meeting with Mr. Krishna & SCGJ to discuss the features to be added to application
Pitch in our proposal to conduct the sessions on life skills
Backlog refinement for the applciation
Finalise the date of training for the application and create a proposal for the same
Discuss with SCGJ to create deck/presentations on the financial schemes that will be shared by NSKFDC

## CRs Post 12th October Release
Change Requests post 12th October 2018 Release
SCGJ | Generate Credentials | Generated Credentials table to be populated as soon as the credential is generated
Add column for target allocated before generated on column in generated credentials table
Change password functionality for training partner
| FAQs | dynamic FAQs for SCGJ
| Mail to SCGJ | Mail should be sent to SCGJ as soon as a training partner uploads any document along with the uploaded documents
| Upcoming assessments | Details of the upcoming assessments to be shown to SCGJ for each training partner
| SCGJ - Master Sheet Import | Skill Council can access the master sheets uploaded by the training partners
The master sheet of the batch should also contain a pay out to candidates field which will be filled by Kamal
| SCGJ - Generate Final Batch Report | SCGJ can generate the final batch report once the information of pay-out is present in the system
Training Partner | Master Sheet Import | Master Sheet Import history
| Generate Reports | Add column for view/download reports from audit table
NSKFDC | Waste Pickers Data | Discussion required to make the system flexible for Waste Pickers as well as Safai Karamcharis