## Sheet1 (hidden)
NSKFDC Product Backlog
Screen | Epic Id | Epic | Story Id | Story | Story Point | Owner | ETA
Training Partner | EP-1 | Login | NSKFDC-1 | As a Product Owner, I want a login page of the application so that, I can login to the application using valid username and password
|  |  | NSKFDC-2 | As a Product Owner, I want the designs of the login page as agreed in the GD
|  |  | NSKFDC-3 | As a Product Owner, I want front end validations on username and password fields of the login page
|  |  | NSKFDC-4 | As a Product Owner, I want role based routings so that the user can be redirected to the appropriate page as per his/her role
|  |  | NSKFDC-5 | As a Product Owner, I want a show password icon along the password field so that, when I click on it the password can be seen
| EP-2 | Generate Batch Reports | NSKFDC-6 | As a Product Owner, I want the look and feel of the application to be the same as agreed in the GD
|  |  | NSKFDC-7 | As a Product Owner, I want a dropdown for batch id which contains a list of batch id against the specific training partner so that, the user can choose the batch id for which the report has to be generated
|  |  | NSKFDC-8 | As a Product Owner, I want to add 2 photographs of each day so that the resulting batch report should have the photographs that are uploaded day wise
|  |  | NSKFDC-9 | As a Product Owner, I want the format of pdf to be generated from the system to be specified so that it can be generated from the system
|  |  | NSKFDC-10 | As a Product Owner, I want a generate report button so that when I have uploaded the photographs and I click on the generate button, the report is generated and downloaded in zip file
|  |  | NSKFDC-11 | As a Product Owner, I want a search report functionality so that when I enter the batch id and click on search button, the reports with the specific batch id appears
| EP-3 | Data Import | NSKFDC-12 | As a Product Owner, I want a data import functionality in the application so that, I can feed data into the system against a specific batch id
|  |  | NSKFDC-13 | As a product owner I want a generate batch button so that when I click on it, a new batch with batch Id(auto generated) is created in the database and the excel sheet for that batch with required information is downloaded
|  |  | NSKFDC-14 | As a Product Owner, I want the look and feel of the Import functionality to be the same as that of GD
|  |  | NSKFDC-15 | As a Product Owner, I want the statistics to be updated on reloading the page when the values in the database are updated so that, only updated information is available in the panel
|  |  | NSKFDC-16 | As a Product Owner, I want a batch id dropdown in Existing batch section so that it displays all the list of batch ids that have been generated for that particular training partner
|  |  | NSKFDC-17 | As a Product Owner, I want text fields as given in GD so that I only have to enter the given details once (At different time intervals) while uploading the batch sheet
|  |  | NSKFDC-18 | As a Product Owner, I want the text fields to be disabled so that the user cannot enter details until he/she selects the batch id
|  |  | NSKFDC-19 | As a Product Owner, I want a type check on the file to be uploaded so that the file is only of .csv type
|  |  | NSKFDC-20 | As a Product Owner, I want the records in the database to be updated when the user enters a batch file against a specific batch Id so that, the information can be filled at different intervals
|  |  | NSKFDC-21 | As a Product Owner, I want the text fields under update existing batch to show information that has already been updated by the user, so that he does not enter the information again
| EP-4 | Generate Reports | NSKFDC-22 | As a Product Owner, I want a Generate Report Functionality so that I can generate the reports in PDF and Excel format against the specified batch id
|  |  | NSKFDC-23 | As a Product Owner, I want the look and feel of the application to be the same as agreed in the GD
|  |  | NSKFDC-24 | As a Product Owner, I want the reports to be generated against a specific batch Id so that only the information of the particular batch is given in the report
|  |  | NSKFDC-25 | As a Product Owner, I want a drop down showing the list of reports that can be generated so that I can have a list of reports to choose from
|  |  | NSKFDC-26 | As a Product Owner, I want a generate report button so that a report is generated and downloaded when the generate button is clicked
|  |  | NSKFDC-27 | As a Product Owner, I want a search report functionality so that when I enter the batch id and click on search button, the reports with the specific batch id appears
|  |  | NSKFDC-28 | As a Product Owner, I want a report generation history table so that, the generated reports can be seen in the table
|  |  | NSKFDC-29 | As a Product Owner, I want to be able to view the generated report by clicking on the PDF icon in the search report and history table of the functionality
| EP-5 | Upload Documents | NSKFDC-30 | As a Product Owner, I want the look and feel of the application to be the same as agreed in the GD
|  |  | NSKFDC-31 | As a Product Owner, I want a dropdown which shows the list of documents that can be uplaoded on the application so that I can choose the document from the given list
|  |  | NSKFDC-32 | As a Product Owner, I want a batch Id field to be populated when I select the document type so that I can enter the batch id against which the document is to be uploaded
|  |  | NSKFDC-33 | As a Product Owner, I want an upload button, so that when I click on it the file gets uploaded into the system
|  |  | NSKFDC-34 | As a Product Owner, I want an upload history table so that, I can see the reports that have been uploaded into the system
|  |  | NSKFDC-35 | As a Product Owner, I want a search document functionality so that when I enter the batch id and click on search button the result for the given batch id appears in the table
SCGJ Admin | EP-6 | Dashboard | NSKFDC-36 | As a Product Owner, I want a Dashboard page of the application so that, All the important statistics are available on the dashboard
|  |  | NSKFDC-37 | As a Product Owner, I want a the designs of the Dashboard to be the same as that of GD, so that it looks the same as GD
|  |  | NSKFDC-38 | As a Product Owner, I want the statistics to be updated on reloading the page when the values in the database are updated so that, only updated information is available on the dashboard
|  |  | NSKFDC-39 | As a Product Owner, I want to download the high charts in different formats so that, I can use these charts in my reports or documentations
|  |  | NSKFDC-40 | As a Product Owner, I want the information available on the dashboard design to be the same as agreed in the GD so that, I can have updated information about the same
|  |  | NSKFDC-41 | As a Product Owner, I want the infographs to be updated on reloading the page when the values in the database are updated so that, only updated information is available on the dashboard
| EP-7 | FAQs | NSKFDC-42 | As a Product Owner I want the look and feel of the application to be the same as agreed in the graphic designs
|  |  | NSKFDC-43 | As a Product Owner, I want static as well as user selected values for questions in the FAQ section so that I can modify the questions as per my needs
|  |  | NSKFDC-44 | As a Product Owner, I want that when I click on the plus(+) sign of any question then a panel should open and the results should be available from the backend
|  |  | NSKFDC-45 | As a Product Owner, I want user selected values in my questions so that I can modify my question as per my needs and get the results for the same
| EP-8 | View Documents | NSKFDC-46 | As a Product Owner, I want the look and feel of the application to be the same as agreed in the GD
|  |  | NSKFDC-47 | As a Product Owner, I want a search document functionality so that when I enter name of training partner and its batch ID or SCGJ Batch Number and click on submit button, I can view a zip file which contains all the files uploaded by the training partner for that batch id
|  |  | NSKFDC-48 | As a Product Owner, I want when I click on the zip icon of the result, the file should be downloaded so that, I can view the files uploaded by the training partner
| EP-9 | Generate Credentials | NSKFDC-49 | As a Product Owner, I want the look and feel of the application to be the same as agreed in the GD
|  |  | NSKFDC-50 | As a Product Owner, I want to generate credentials for the training partner so that, the training partner can login to the application
|  |  | NSKFDC-51 | As a Product Owner, I want front end validations on the fields given in generate credential section so that the input in each field is in correct format and should not be left blank
|  |  | NSKFDC-52 | As a Product Owner, I want a generate credentials button so that, when I enter all the details in correct format and click on henerate credentials button the details are stored in the database
|  |  | NSKFDC-53 | As a Product Owner, I want that once the credentials are generated the training partner can login to the application using its credentials that are generated by the admin
|  |  | NSKFDC-54 | As a Product Owner, I want a Generated Credentials section so that I can search the credentials that were generated by the admin
|  |  | NSKFDC-55 | As a Product Owner, I want when I eenter the name of training partner under generated credentials section and click on search button, then if the record is present in the database, it appears in the table |  |  | #NAME?

## Track 1 - NSKFDC - Login
Epic | Story Id | Story | Owner |  | Mentor
Login | NSKFDC-1 | As a Product Owner, I want a login page of the application so that, I can login to the application using valid username and password | Ayush Jain | Done
| NSKFDC-2 | As a Product Owner, I want the designs of the login page as agreed in the GD
| NSKFDC-3 | As a Product Owner, I want front end validations on username and password fields of the login page
| NSKFDC-4 | As a Product Owner, I want role based routings so that the user can be redirected to the appropriate page as per his/her role
| NSKFDC-5 | As a Product Owner, I want a show password icon along the password field so that, when I click on it the password can be seen
View Documents | NSKFDC-6 | As a Product Owner, I want the look and feel of the application to be the same as agreed in the GD | Bhawana | Bug Fixing
| NSKFDC-7 | As a Product Owner, I want a search document functionality so that when I enter name of training partner and its batch ID or SCGJ Batch Number and click on submit button, I can view a zip file which contains all the files uploaded by the training partner for that batch id
| NSKFDC-8 | As a Product Owner, I want when I click on the zip icon of the result, the file should be downloaded so that, I can view the files uploaded by the training partner
Generate Credentials | NSKFDC-9 | As a Product Owner, I want the look and feel of the application to be the same as agreed in the GD | Juli | Done
| NSKFDC-10 | As a Product Owner, I want to generate credentials for the training partner so that, the training partner can login to the application
| NSKFDC-11 | As a Product Owner, I want front end validations on the fields given in generate credential section so that the input in each field is in correct format and should not be left blank
| NSKFDC-12 | As a Product Owner, I want a generate credentials button so that, when I enter all the details in correct format and click on henerate credentials button the details are stored in the database
| NSKFDC-13 | As a Product Owner, I want that once the credentials are generated the training partner can login to the application using its credentials that are generated by the admin
| NSKFDC-14 | As a Product Owner, I want a Generated Credentials section so that I can search the credentials that were generated by the admin
| NSKFDC-15 | As a Product Owner, I want when I eenter the name of training partner under generated credentials section and click on search button, then if the record is present in the database, it appears in the table

## Track 2 - NSKFDC
Epic | Story Id | Story | Owner | ETA
Data Import | NSKFDC-16 | NOT REQUIRED
| NSKFDC-17 | As a product owner I want a generate batch button so that when I click on it, a new batch with batch Id(auto generated) is created in the database and the excel sheet for that batch with required information is downloaded (FE+BE) | Pranjal Mani | Bug Fixing
| NSKFDC-18 | As a Product Owner, I want the look and feel of the Import functionality to be the same as that of GD | Sagun | Bug Fixing
| NSKFDC-19 | As a Product Owner, I want the statistics to be updated on reloading the page when the values in the database are updated so that, only updated information is available in the panel
| NSKFDC-20 | As a Product Owner, I want a batch id dropdown in Existing batch section so that it displays all the list of batch ids that have been generated for that particular training partner | Akash | Done
| NSKFDC-21 | As a Product Owner, I want text fields as given in GD so that I only have to enter the given details once (At different time intervals) while uploading the batch sheet |  | Done
| NSKFDC-22 | As a Product Owner, I want the text fields to be disabled so that the user cannot enter details until he/she selects the batch id |  | Done
| NSKFDC-23 | As a Product Owner, I want a type check on the file to be uploaded so that the file is only of xlsx type |  | Done
| NSKFDC-24 | As a Product Owner, I want the records in the database to be updated when the user enters a batch file against a specific batch Id so that, the information can be filled at different intervals |  | Left
| NSKFDC-25 | As a Product Owner, I want the text fields under update existing batch to show information that has already been updated by the user, so that he does not have to enter the information again |  | Done

## Track 3 - NSKFDC
Epic | Story Id | Story | Owner | ETA
Generate Batch Report | NSKFDC-26 | As a Product Owner, I want the look and feel of the application to be the same as agreed in the GD | Samridhi | Done
| NSKFDC-27 | As a Product Owner, I want a dropdown for batch id and a text field to enterthe SCGJ batch number which contains a list of batch id against the specific training partner so that, the user can choose the batch id for which the report has to be generated |  | Done
| NSKFDC-28 | As a Product Owner, I want to add 2 photographs of each day so that the resulting batch report should have the photographs that are uploaded day wise |  | TO Do
| NSKFDC-29 | As a Product Owner, I want the format of pdf to be generated from the system to be specified so that it can be generated from the system |  | Done
| NSKFDC-30 | As a Product Owner, I want a generate report button so that when I have uploaded the photographs and I click on the generate button, the report is generated and downloaded |  | Done
| NSKFDC-31 | As a Product Owner, I want a search report functionality so that when I enter the batch id and click on search button, the reports with the specific batch id appears | Shivangi | Out of Scope
Generate Reports | NSKFDC-32 | As a Product Owner, I want the look and feel of the functionality to be the same as agreed in the GD | Shivangi | Done
| NSKFDC-33 | As a Product Owner, I want to generate the .pdf format of occupation certificate when I select the occupation certificate option from dropdown and enter the batch ID for which the report has to be generated | Mannu
| NSKFDC-34 | As a Product Owner, I want the .pdf format of attendance sheet to be generated when I select the the attendance sheet option from the dropdown and enter the batch ID for which the report has to be generated | Mannu
| NSKFDC-35 | Asa Product Owner, I want the .pdf format of minutes of selection committee meeting to be generated when I select the respective option from the dropdown and enter the batch ID | Shivangi
| NSKFDC-36 | As a Product Owner, I want the .xl format of the NSKFDC sheet to be generated when I enter the batch id for which I want to generate the excel sheet for the nskfdc platform | Mannu
| NSKFDC-37 | As a Product Owner, I want the .xl format of the SDMS sheet to be generated when I enter the batch id for which I want to generate the excel sheet for the nskfdc platform | Shivangi

## Track 4 - NSKFDC
Epic | Story Id | Story | Owner | ETA
Upload Documents | NSKFDC-38 | As a Product Owner, I want the look and feel of the application to be the same as agreed in the GD (FE of Upload Doc) | Abhishek
| NSKFDC-39 | As a Product Owner, I want a dropdown which shows the list of documents that can be uplaoded on the application so that I can choose the document from the given list
| NSKFDC-40 | As a product owner, I want the batch ID dropdown to be pre-populated with the batch ID that are there for the specific training partner so that, I can select the batch Id against which I want to upload the document
| NSKFDC-41 | As a Product Owner, I want a batch Id field and SCGJ batch ID (for final batch report) to be populated when I select the document type so that I can enter the batch id against which the document is to be uploaded
| NSKFDC-42 | As a Product Owner, I want an upload button, so that when I click on it the file gets uploaded into the system
| NSKFDC-43 | As a Product Owner, I want a search document functionality so that when I enter the batch id and click on search button the result for the given batch id appears in the table (FE +BE) | Sarthak
Dashboard | NSKFDC-44 | As a Product Owner, I want a Dashboard page of the application so that, All the important statistics are available on the dashboard (BE of stats block) | Shivanshu | Done
| NSKFDC-45 | As a Product Owner, I want a the designs of the Dashboard to be the same as that of GD, so that it looks the same as GD (ALL FE WORK) | Sarthak
| NSKFDC-46 | As a Product Owner, I want a bar chart representing the top 5 states with maximum training centers so that, I can get to know which states have the maximum training centers | Aman
| NSKFDC-47 | As a Product Owner, I want a bar chart representing the total candidates trainined in each month for the last 6 months , so that I can get the information of the number of candidates trained in each month | Shivanshu
| NSKFDC-48 | As a Product Owner, I want a map of India dynamically representing the number of training partners in each state so that when I hover my mouse on any states then the number of training partners can be displayed | Aman
FAQs | NSKFDC-49 | As a Product Owner I want the look and feel of the application to be the same as agreed in the graphic designs | Out of scope
| NSKFDC-50 | As a Product Owner, I want static as well as user selected values for questions in the FAQ section so that I can modify the questions as per my needs
| NSKFDC-51 | As a Product Owner, I want that when I click on the plus(+) sign of any question then a panel should open and the results should be available from the backend
| NSKFDC-52 | As a Product Owner, I want user selected values in my questions so that I can modify my question as per my needs and get the results for the same

## Remaining Work
Story ID | Description | Work Left | Owner | Estimate
NSKFDC - 7 | As a Product Owner, I want a search document functionality so that when I enter name of training partner and its batch ID or SCGJ Batch Number and click on submit button, I can view a zip file which contains all the files uploaded by the training partner for that batch id | Bug Fixing | Pooja
NSKFDC - 8 | As a Product Owner, I want when I click on the zip icon of the result, the file should be downloaded so that, I can view the files uploaded by the training partner
NSKFDC - 17 | As a product owner I want a generate batch button so that when I click on it, a new batch with batch Id(auto generated) is created in the database and the excel sheet for that batch with required information is downloaded (FE+BE) | Bug Fixing | Priyanka
NSKFDC - 24 | As a Product Owner, I want the records in the database to be updated when the user enters a batch file against a specific batch Id so that, the information can be filled at different intervals | To Do | Prateek
NSKFDC - 19 | As a Product Owner, I want the statistics to be updated on reloading the page when the values in the database are updated so that, only updated information is available in the panel | Bug Fixing - Financial Year | Pooja
NSKFDC - 28 | As a Product Owner, I want to add 2 photographs of each day so that the resulting batch report should have the photographs that are uploaded day wise | To Do | Priyanka
NSKFDC - 42 | As a Product Owner, I want an upload button, so that when I click on it the file gets uploaded into the system | To Do | Prateek
| Populate the name of training partner on their template | Bug fixing | Priyanka
Number of Stories - 7
Change Request
Functionality to change the password for the existing training partner - Pooja
Maintain History for Master Sheet Import - Pooja
Light box to be implemented on Admin Dashboard - When user clicks on upcoming assessments then details of the batches should be shown - Priyanka
Change Requests - 2