## Sheet1
Not Started | Issue ID | Work Plan - Priyanka | ETA(in hours) | STATUS(with Time logged) | Delay | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
In Progress | NA-1 | Populate the Training Partner name on the TP table ¦ 2 hrs | 2 | 0 | 2
In QA | NA-22 | Selection Committee date should not get populated as null ¦ 1.5 hrs | 1.5 | 1.5 | 0
Done | NA-27 | Type of file while browsing for image should be jpeg, png not all files ¦ 0.75 hrs | 0.75 | 0.5 | 0.25
| NA-39 | Cells are not blocked ¦ Excel sheet in Generated Batch Id ¦ 2.25 hrs | 2.25 |  | 2.25
| NA-40 | Complete Name of Job role not populated in generated Batch Id excel Sheet ¦ 1.5 hrs | 1.5 |  | 1.5
| NA-41 | Submit User Input Data ¦ Master Sheet Import ¦ 3 hrs | 3 | 4 | -1
| NA-43 | Excel sheet Should have batchId in its name ¦ Generate batch ¦ 1.5 hrs | 1.5 |  | 1.5
| NA-29 | In Generate Batch report, user should be able to choose two images on one browse ¦ 1.5 hrs | 1.5 | 0.5 | 1
| NA-32 | Disable browse button when Batch Id & Scgj Batch number not selected ¦ 0.75 hrs | 0.75 | 0.5 | 0.25
| NA-36 | On browse, selected image name should be visible in text field ¦ 0.75 hrs | 0.75 | 1 | -0.25
| NA-38 | Batch Report Generation ¦ 7.5 hrs | 7.5 |  | 7.5
| NA-14 | Download Zip not working for some batchId ¦ 3 hrs | 3 |  | 3
| NA-87 | Integration Testing ¦ 3hrs | 3 |  | 3
| NA-96 | JIRA Monitoring |  | 2
|  |  | 29 | 10 | 19
| Issue ID | Work Plan - Pooja | ETA(in hours) | STATUS(with Time logged) |  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
| NA-85 | Creation of Dump Data ¦ 2 hrs | 2 |  | 2 | bar: 30
| NA-13 | Frontend cosmetic fixes ¦ Generate Credentials ¦ 2 hr. 30 min | 2.5 | 2.75 | -0.25 | bar: 25
| NA-42 | Frontend validation ¦ View documents ¦ 45 min | 0.75 | 0.75 | 0 | bar: 25; 30
| NA-60 | SCGJ batch number field alignment ¦ Generate batch report ¦ 45 min | 0.75 | 0.75 | 0 | bar: 25
| NA-63 | No guidelines in Upload documents ¦ 3 hr. | 3 |  | 3 | bar: 26
| NA-31 | NSDC registration number check ¦ 1 hr. 30 min | 1.5 | 3 | -1.5 | bar: 25
| NA-69 | No validation when there is no data regarding batch id ¦ Upload documents ¦ 45 Min | 0.75 | 0.75 | 0 | bar: 26
| NA-72 | Updated Targets ¦ frontend ¦ 1.5 hrs | 1.5 |  | 1.5 | bar: 26
| NA-71 | Recent generated batch not populating in dropdown ¦ Master sheets import ¦ 45 min | 0.75 | 0.75 | 0 | bar: 26
| NA-70 | Candidates trained ¦ dashboard ¦ 4 hr. 30 min | 4.5 |  | 4.5 | bar: 27
| NA-58 | Generated report not populating in single click ¦ Generate Report ¦ 1 hr. 30 min | 1.5 |  | 1.5 | bar: 27
| NA-59 | Favicon ¦ SCGJ logo ¦ 45 min | 0.75 | 0.5 | 0.25 | bar: 25
|  |  | 20.25 | 9.25 | 11
| Issue ID | Work Plan - Prateek | ETA(in hours) | STATUS(with Time logged) |  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
| NA-2 | Upload Documents - Training Partner ¦ 7.5 Hrs | 7.5 |  | 7.5 | bar: 27 to 28
| NA-86 | Handover the Project to SCGJ ¦ 6 hrs | 6 |  | 6 | bar: 2
| NA-72 | Update Targets Functionality - Admin ¦ Back end ¦ 2.5hr | 2.5 |  | 2.5 | bar: 26
| NA-28 | Data Import ¦ Training Partner ¦ 15 hr | 15 |  | 15 | bar: 30 to 31
| NA-12 | Search Functionality ¦ View Documents ¦ 3hr | 3 | 1 | 2 | bar: 25
| NA-92 | Acceptance Criteria ¦ NSKFDC - App ¦ 2 hrs | 2 | 1 | 1 | bar: 25
| NA-93 | PFP Discussion ¦ Revenue Model ¦ Training Identification ¦ 1 hr | 1 | 3 | -2 | bar: 25
| NA-21 | Training Partner Dashboard ¦ Targets ¦ 1 hr | 1 |  | 1 | bar: 26
| NA-18 | Upload Functionality ¦ Data Import ¦ 2 hr | 2 | 3 | -1 | bar: 26
| NA-95 | SCGJ Proposal Discussion ¦ Business Opportunities - 1 Hr | 1 |  | 1 | bar: 26
|  |  | 41 | 8 | 33
| NA-84 | Deploy NSKFDC App on AWS ¦ Pranjal | 3 |  | 3