## Priyanka
Issue ID | Work Plan - Priyanka | ETA | STATUS | Time Required | F 27 | 28 | 29 | M 30 | T 31 | W 1 | Th 2 | F 3 | 4 | 5 | M 6
NA-1 | Populate the Training Partner name on the TP table ¦ 2 hrs | 2 |  | 2 | W 1: NA-1
NA-39 | Cells are not blocked ¦ Excel sheet in Generated Batch Id ¦ 2.25 hrs | 2.25 |  | 2.25 | W 1: NA-39
NA-40 | Complete Name of Job role not populated in generated Batch Id excel Sheet ¦ 1.5 hrs | 1.5 |  | 1.5 | T 31: NA-40
NA-43 | Excel sheet Should have batchId in its name ¦ Generate batch ¦ 1.5 hrs | 1.5 |  | 1.5 | M 30: NA-43
NA-38 | Batch Report Generation ¦ 7.5 hrs | 7.5 |  | 7.5 | F 27: NA-38; M 30: NA-38
NA-14 | Download Zip not working for some batchId ¦ 3 hrs | 3 |  | 3 | T 31: NA-14
NA-21 | Training Partner Dashboard ¦ Targets ¦ 1 hr | 1 |  | 1
NA-22 | Selection Committee date should not get populated as null ¦ 1.5 hrs | 1.5 | 1.5 | 0
NA-27 | Type of file while browsing for image should be jpeg, png not all files ¦ 0.75 hrs | 0.75 | 0.75 | 0
NA-41 | Submit User Input Data ¦ Master Sheet Import ¦ 3 hrs | 3 | 3 | 0
NA-29 | In Generate Batch report, user should be able to choose two images on one browse ¦ 1.5 hrs | 1.5 | 1.5 | 0
NA-32 | Disable browse button when Batch Id & Scgj Batch number not selected ¦ 0.75 hrs | 0.75 | 0.75 | 0
NA-36 | On browse, selected image name should be visible in text field ¦ 0.75 hrs | 0.75 | 0.75 | 0
NA-96 | JIRA Monitoring ¦ 1 hr per day |  |  |  | NA-96 |  |  | NA-96 | NA-96 | NA-96 | NA-96 | NA-96 |  |  | NA-96
QRENCIA-392 | Technology sessions |  |  |  | F 27: QRENCIA-392; M 30: QRENCIA-392; T 31: QRENCIA-392
|  | 27 | 8.25 | 18.75 | bar: F 27; M 30 to F 3; M 6
NA-87 | Integration Testing ¦ 3hrs | 3 |  | 3 | F 3: NA-87
| TOTAL DEVELOPMENT HOUR(5 hours per day) | 20
| Total Work assigned | 19
NA-84 | Deploy NSKFDC App on AWS ¦ Pranjal

## Pooja
Issue ID | Work Plan - Pooja | ETA | STATUS | Time Required | F 27 | 28 | 29 | M 30 | T 31 | W 1 | Th 2 | F 3 | 4 | 5 | M 6
NA-63 | No guidelines in Upload documents ¦ 3 hr. | 3 |  | 3 | W 1: NA-63
NA-72 | Updated Targets ¦ frontend ¦ 1.5 hrs | 1.5 |  | 1.5 | W 1: NA-72
NA-58 | Generated report not populating in single click ¦ Generate Report ¦ 1 hr. 30 min | 1.5 |  | 1.5 | F 27: NA-58
NA-2 | Upload Documents - Training Partner ¦ 11.5 Hrs | 11.5 |  | 11.5 | F 27: NA-2; M 30: NA-2; T 31: NA-2; W 1: NA-2
NA-97 | Zip file download Validation ¦ View Documents | 0.75 |  | 0.75 | F 27: NA-97
NA-13 | Frontend cosmetic fixes ¦ Generate Credentials ¦ 2 hr. 30 min | 2.5 | 2.5 | 0
NA-42 | Frontend validation ¦ View documents ¦ 45 min | 0.75 | 0.75 | 0
NA-60 | SCGJ batch number field alignment ¦ Generate batch report ¦ 45 min | 0.75 | 0.75 | 0
NA-31 | NSDC registration number check ¦ 1 hr. 30 min | 1.5 | 1.5 | 0
NA-69 | No validation when there is no data regarding batch id ¦ Upload documents ¦ 45 Min | 0.75 | 0.75 | 0
NA-71 | Recent generated batch not populating in dropdown ¦ Master sheets import ¦ 45 min | 0.75 | 0.75 | 0
NA-70 | Candidates trained ¦ dashboard ¦ 4 hr. 30 min | 4.5 | 4.5 | 0
NA-59 | Favicon ¦ SCGJ logo ¦ 45 min | 0.75 | 0.75 | 0
QRENCIA-392 | Technology sessions |  |  |  | F 27: QRENCIA-392; M 30: QRENCIA-392; T 31: QRENCIA-392
|  | 30.5 | 12.25 | 18.25 | bar: F 27; M 30 to F 3; M 6
NA-85 | Creation of Dump Data ¦ 2 hrs | 2 |  | 2 | F 27: SHIVANSHU
| TOTAL DEVELOPMENT HOUR(6 hours per day) | 25
| Work assigned | 19

## Prateek
Issue ID | Work Plan - Prateek | ETA | STATUS | Time Required | F 27 | 28 | 29 | M 30 | T 31 | W 1 | Th 2 | F 3 | 4 | 5 | M 6
NA-28 | Data Import ¦ Training Partner ¦ 15 hr | 15 |  | 15 | F 27: NA-28; M 30: NA-28; T 31: NA-28; W 1: NA-28; Th 2: NA-28
NA-98 | Document Guidelines for Upload Documents | 0.5 |  | 0.5 | F 27: NA-98
NA-99 | Creating Design for Update Targets | 0.5 |  | 0.5 | F 27: NA-99
NA-72 | Update Targets Functionality - Admin ¦ Back end ¦ 2.5hr | 2.5 | 2.5 | 0
NA-12 | Search Functionality ¦ View Documents ¦ 3hr | 3 | 3 | 0
NA-18 | Upload Functionality ¦ Data Import ¦ 2 hr | 2 | 2 | 0
QRENCIA-392 | Technology sessions |  |  |  | F 27: QRENCIA-392; M 30: QRENCIA-392; T 31: QRENCIA-392
|  | 23.5 | 7.5 | 16 | bar: F 27; M 30 to F 3; M 6
NA-86 | Handover the Project to SCGJ ¦ 6 hrs | 6 |  | 6 | Th 2: NA-86; F 3: NA-86; M 6: NA-86
| TOTAL DEVELOPMENT HOUR(4 hours per day) | 16
| Work assigned | 16

## Pranjal
Issue ID | Work Plan - Pranjal | ETA | STATUS | Time Required | Th 2 | F 3 | 4 | 5 | M 6
NA-84 | Deploy NSKFDC App on AWS ¦ 3hr | 3 |  | 3 | NA-84 |  |  |  | NA-84